# District 24-L Global Extension Team (GET) Action Plan

Area of Focus: MISSION 1.5 / Membership Development – New Clubs

## Goal Statement

By June 30, 2027, District 24-L will charter at least one new Lions club by establishing and activating a District Global Extension Team (GET), identifying communities with strong potential for Lions growth, conducting community outreach and recruitment, and supporting prospective members through the new club development and charter process.

### Action Steps

| Action Step | Responsible Party | Required Resources | Begin | Due Date |
| --- | --- | --- | --- | --- |
| 1. Establish the District 24-L Global Extension Team (GET). Confirm the GET Coordinator and recruit a working team representing district leadership and membership development. | DG, GET Coordinator | DG, VDGs, Zone Chairs, club membership leaders; DG goals and action plan | 7/15/2026 | 9/19/2026 |
| 2. Conduct an initial GET planning meeting. Review the DG goal of one new club, establish team expectations, assign responsibilities, and establish a regular meeting/check-in schedule. | GET Coordinator, DG | District membership data, DG goals, action plan, meeting platform | 9/15/2026 | 9/30/2026 |
| 3. Identify areas of opportunity for a new Lions club. Review communities currently underserved by Lions, demographic trends, community needs, existing clubs, potential partners, and possible club types/formats. Develop a shortlist of 3–5 priority communities. | GET Coordinator, GET members, Zone Chairs | Membership reports, community assessment information, local demographic information, New Club Development resources | 9/1/2026 | 10/30/2026 |
| 4. Select the primary target community. Evaluate the priority communities and select at least one location for concentrated new-club development. Identify a secondary location if the first opportunity does not develop as anticipated. | GET Coordinator, DG, GET | Community assessment, GET recommendations, district leadership input | 7/15/2026 | 12/15/2026 |
| 5. Build a community asset and prospect list. Identify community leaders, businesses, nonprofits, schools, faith communities, civic organizations and individuals who may become partners, referral sources or prospective members. | GET members, Zone Chairs, local Lions | Community contacts, asset map, prospect tracking system, local Lions connections | 9/20/2026 | 1/31/2027 |
| 6. Conduct community outreach and recruitment. Meet with community leaders and potential partners, make personal invitations, conduct service-focused recruitment activities, and develop a pool of prospective charter members. | GET Coordinator, GET, Zone Chairs, sponsoring Lions/clubs | Recruitment materials, presentations, prospect list, marketing/social media support | 9/15/2027 | 4/30/2027 |
| 7. Hold a new club informational meeting. Invite prospects to learn about Lions, discuss community needs and service opportunities, and explain the benefits and expectations of membership. | GET Coordinator, GET | Meeting location/platform, invitations, Lions information, prospective-member contact list | 10/1/2026 | 5/15/2027 |
| 8. Develop the prospective club and hold an organizational meeting. Follow up individually with prospects, secure commitments, identify potential officers and determine the club's initial service priorities. | GET Coordinator, GET, Guiding Lion(s) | Prospect tracking, organizational meeting materials, New Club Development Guide | 8/1/2026 | 6/30/2027 |
| 9. Complete the charter process for at least one new District 24-L Lions club. Work with prospective members and district leadership to complete required charter documentation and prepare the club for launch. | GET Coordinator, DG, GET, Guiding Lion(s) | Charter application/resources, member information, Lions International support | 11/1/2026 | 6/1/2027 |
| 10. Support the new club for long-term success. Connect the club with Guiding Lion support, officer training, orientation, district resources and its first visible community service activity. | Guiding Lion(s), GET Coordinator, DG | Guiding Lion resources, officer/member orientation, district/GMA resources | Upon charter | + 2 Years |

## Assessment

The GET Coordinator will provide regular progress updates to the District Governor and district leadership. Progress will be measured by:

- GET established and actively meeting.

- Priority communities identified and evaluated.

- One primary new-club location selected.

- Community partners and prospective members identified.

- Recruitment contacts and follow-up activities documented.

- Informational and organizational meetings conducted.

- Prospective charter members developed.

- At least one new Lions club chartered by November 1, 2026.

- Guiding Lion and post-charter support established.

The GET will review the action plan regularly and adjust activities, responsibilities, target communities, or timelines when progress indicates changes are necessary.